## Secure Access & Priv Control
Cybersecurity Program
Secure Access & Privileged Control - Detailed Project Plan
Timeline: Jun 2026 - Apr 2028 ¦ 3 Roadmap Phases run in parallel, organized into 8 work categories ¦ ~308 working days of effort ¦ Rows in pink = newly added tasks ¦ Built 8/20/2026
Activity ID | Activity | Scope | Responsible User | Execution Owner | Start Date | End Date | Status | Roadblock/ Dependencies
ROADMAP PHASE 1 - CONDITIONAL ACCESS REVIEW / UPDATE (Jul 2026 - Jun 2027)
Category 1 - Application Inventory & Criticality
Export the full application list from LeanIX
PAM - P1.1 | Export the full application list from LeanIX | LeanIX | Sag | TBD | 2026-07-27 | 2026-08-07 | Completed
Validate completeness (reconcile vs Entra enterprise apps / SSO list)
PAM - P1.2 | Write the Application Criticality & Classification Standard | LeanIX / Governance | Sag | TBD | 2026-07-27 | 2026-08-28 | In_Review | Draft shared 7/30; shorter version 8/11; LeanIX review meeting scheduled per 8/12 note
PAM - P1.3 | Export Entra enterprise application list | Entra ID | Sag | TBD | 2026-08-24 | 2026-08-24 | TO DO
PAM - P1.4 | Export current SSO application list | Entra ID / IdP | Sag | TBD | 2026-08-25 | 2026-08-25 | TO DO
PAM - P1.5 | Compare LeanIX against Entra enterprise applications | LeanIX / Entra | Sag | TBD | 2026-08-26 | 2026-08-26 | TO DO | After P1.1, P1.3
PAM - P1.6 | Compare LeanIX against SSO application list | LeanIX / IdP | Sag | TBD | 2026-08-27 | 2026-08-27 | TO DO | After P1.4
PAM - P1.7 | Document missing, duplicate, and unmatched applications | LeanIX | Sag | TBD | 2026-08-28 | 2026-08-28 | TO DO
PAM - P1.8 | Review reconciliation exceptions with LeanIX and Entra teams | LeanIX / Entra | Sag | TBD | 2026-08-31 | 2026-08-31 | TO DO | Dep: LeanIX & Entra teams
Define the criticality criteria & scoring scale
PAM - P1.9 | Define business criticality criteria | Governance | Sag | TBD | 2026-08-24 | 2026-08-25 | TO DO | Builds on Standard (P1.2)
PAM - P1.10 | Define scoring scale and criticality thresholds | Governance | Sag | TBD | 2026-08-26 | 2026-08-27 | TO DO
PAM - P1.11 | Application Questionnaire | LeanIX Survey | Sag | TBD | 2026-08-17 | 2026-08-20 | In_Progress
PAM - P1.12 | Review and approve the criticality method | Security Governance | Sag | TBD | 2026-08-28 | 2026-08-31 | TO DO
Finalize & send the owner questionnaire (with follow-up/escalation plan)
PAM - P1.13 | Finalize Application Questionnaire | LeanIX Survey | Sag | TBD | 2026-08-20 | 2026-08-20 | In_Progress | Hard deadline: prep complete today 8/20
PAM - P1.13a | Package & hand over questionnaire to LeanIX team (format, target list, instructions) | LeanIX team | Sag | TBD | 2026-08-20 | 2026-08-20 | TO DO | [NEW] Dep: LeanIX team - handover today 8/20
PAM - P1.14 | Confirm application owner respondent list | LeanIX / App owners | Sag | TBD | 2026-08-20 | 2026-08-20 | TO DO
PAM - P1.15 | Send questionnaire to application owners (distributed by LeanIX team) | LeanIX team | Sag | LeanIX Team | 2026-08-21 | 2026-08-21 | TO DO | HARD DEADLINE 8/21 - LeanIX team must distribute; escalate same-day if not sent
PAM - P1.16 | Track responses and send reminders | LeanIX Survey | Sag | TBD | 2026-08-24 | 2026-09-04 | TO DO | Background thru 9/4
PAM - P1.17 | Escalate overdue or incomplete responses | LeanIX Survey | Sag | TBD | 2026-08-20 | 2026-08-26 | TO DO
Score & rank the apps - identify the top 10
PAM - P1.18 | Validate completed questionnaire responses | LeanIX Survey | Sag | TBD | 2026-09-14 | 2026-09-15 | TO DO | After P1.16/P1.17 responses in
PAM - P1.19 | Calculate and rank application scores | Scoring model | Sag | TBD | 2026-09-16 | 2026-09-17 | TO DO
PAM - P1.20 | Review scoring exceptions with application owners | App owners | Sag | TBD | 2026-09-18 | 2026-09-22 | TO DO
PAM - P1.21 | Identify and approve the top 10 applications | Security Governance | Sag | TBD | 2026-09-23 | 2026-09-24 | TO DO
Record the criticality ratings back into LeanIX
PAM - P1.22 | Prepare approved criticality ratings for LeanIX | LeanIX | Sag | TBD | 2026-10-12 | 2026-10-12 | TO DO
PAM - P1.23 | Load approved ratings into LeanIX | LeanIX | Sag | TBD | 2026-10-13 | 2026-10-13 | TO DO
PAM - P1.24 | Validate updated LeanIX records | LeanIX | Sag | TBD | 2026-10-14 | 2026-10-14 | TO DO
PAM - P1.24a | Resolve failed or rejected updates; set recertification cadence | LeanIX | Sag | TBD | 2026-10-15 | 2026-10-16 | TO DO
NEW - Capture SSO coverage & legacy vs modern auth status per app (roadmap Next Milestone)
PAM - P1.25 | Pull sign-in / authentication method data from Entra per application | Entra ID sign-in logs | Sag | TBD | 2026-08-24 | 2026-08-25 | TO DO | [NEW]
PAM - P1.26 | Classify each app: SSO yes/no; SAML / OIDC / legacy auth | All apps | Sag | TBD | 2026-08-26 | 2026-08-27 | TO DO | [NEW]
PAM - P1.27 | Flag legacy-auth apps as Conditional Access policy input | Entra CA | Sag | TBD | 2026-08-28 | 2026-08-28 | TO DO | [NEW] Feeds P5.11 CA Requirement
PAM - P1.28 | Publish SSO / auth coverage matrix | All apps | Sag | TBD | 2026-08-31 | 2026-08-31 | TO DO | [NEW]
Category 2 - Account & Identity Inventory
Pull all accounts (AD, Entra, apps) and HR / Contractor feeds
PAM - P2.1 | Extract of users from each HR | HR systems | Sag | TBD | 2026-08-24 | 2026-08-25 | Blocked | TBD - confirm blocker & owner
PAM - P2.2 | Extract of users from AD | Active Directory | Sag | Sagar | 2026-07-30 | 2026-08-07 | Completed
PAM - P2.3 | Extract of users from Entra | Entra ID | Sag | Sagar | 2026-07-30 | 2026-08-07 | Completed
PAM - P2.4 | Extract of users from Applications (i.e. EBS) | Applications | Sag | TBD | 2026-08-26 | 2026-08-28 | Blocked | TBD - confirm blocker; dep: app teams
PAM - P2.5 | Extract of contractors from HR contractor feeds | HR contractor feed | Sag | TBD | 2026-08-31 | 2026-09-01 | TO DO
PAM - P2.6 | Extract of entitlement from AD | Active Directory | Sag | Sagar | 2026-07-30 | 2026-08-07 | Completed
PAM - P2.7 | Extract of entitlement from Entra | Entra ID | Sag | Sagar | 2026-07-30 | 2026-08-07 | Completed
PAM - P2.8 | Extract of entitlement from each Applications (i.e. EBS) | Applications | Sag | TBD | 2026-09-02 | 2026-09-04 | Blocked | TBD - confirm blocker; dep: app teams
Tag human vs non-human; correlate human accounts to HR
PAM - P2.9 | Define human and non-human account identification rules | All directories | Sag | TBD | 2026-09-07 | 2026-09-08 | TO DO
PAM - P2.10 | Tag AD, Entra, and application accounts | AD / Entra / Apps | Sag | TBD | 2026-09-09 | 2026-09-14 | TO DO
PAM - P2.11 | Correlate human accounts to HR and contractor records | HR / directories | Sag | TBD | 2026-09-15 | 2026-09-18 | TO DO
PAM - P2.12 | Document unmatched and multiple-match exceptions | Inventory | Sag | TBD | 2026-09-21 | 2026-09-22 | TO DO
PAM - P2.13 | Validate exceptions with HR and platform teams | HR / platform teams | Sag | TBD | 2026-09-23 | 2026-09-25 | TO DO | Dep: HR & platform teams
Identify secondary accounts, link to primary
PAM - P2.14 | Define secondary account identification rules | All directories | Sag | TBD | 2026-09-28 | 2026-09-28 | TO DO
PAM - P2.15 | Identify secondary accounts across AD, Entra, and applications | AD / Entra / Apps | Sag | TBD | 2026-09-29 | 2026-10-01 | TO DO
PAM - P2.16 | Link secondary accounts to primary identities | Inventory | Sag | TBD | 2026-10-02 | 2026-10-06 | TO DO
PAM - P2.17 | Validate unresolved links with account owners | Account owners | Sag | TBD | 2026-10-07 | 2026-10-09 | TO DO
Classify non-human accounts by type and assign an owner to each
PAM - P2.18 | Define non-human account types | NHI | Sag | TBD | 2026-10-12 | 2026-10-13 | TO DO
PAM - P2.19 | Classify service, shared, API, bot, and workload identities | NHI | Sag | TBD | 2026-10-14 | 2026-10-20 | TO DO
PAM - P2.20 | Assign business and technical owners | NHI | Sag | TBD | 2026-10-21 | 2026-10-27 | TO DO
PAM - P2.21 | Escalate unowned non-human accounts | NHI | Sag | TBD | 2026-10-28 | 2026-10-30 | TO DO
Map non-human account dependencies (what systems/apps use each)
PAM - P2.22 | Identify applications and services using each non-human account | NHI | Sag | TBD | 2026-11-02 | 2026-11-05 | TO DO
PAM - P2.23 | Identify integrations, jobs, and credential dependencies | NHI | Sag | TBD | 2026-11-06 | 2026-11-10 | TO DO
PAM - P2.24 | Validate dependencies with technical owners | Technical owners | Sag | TBD | 2026-11-11 | 2026-11-12 | TO DO
PAM - P2.25 | Document unresolved dependencies | NHI | Sag | TBD | 2026-11-13 | 2026-11-13 | TO DO
Capture MFA status per user by each app
PAM - P2.26 | Extract Entra MFA registration and enforcement data | Entra ID | Sag | TBD | 2026-11-16 | 2026-11-17 | TO DO
PAM - P2.27 | Collect application-level MFA status | Applications | Sag | TBD | 2026-11-18 | 2026-11-20 | TO DO
PAM - P2.28 | Map MFA status to users and applications | Inventory | Sag | TBD | 2026-11-23 | 2026-11-25 | TO DO
PAM - P2.29 | Validate MFA exceptions | Inventory | Sag | TBD | 2026-11-26 | 2026-11-27 | TO DO
Produce the consolidated account inventory
PAM - P2.30 | Normalize and merge HR, AD, Entra, and application extracts | Inventory | Sag | TBD | 2026-11-30 | 2026-12-03 | TO DO
PAM - P2.31 | Add classification, correlation, ownership, dependency, and MFA data | Inventory | Sag | TBD | 2026-12-04 | 2026-12-09 | TO DO
PAM - P2.32 | Perform data-quality review and resolve critical exceptions | Inventory | Sag | TBD | 2026-12-10 | 2026-12-15 | TO DO
PAM - P2.33 | Publish the consolidated account inventory | Inventory | Sag | TBD | 2026-12-16 | 2026-12-17 | TO DO
Category 3 - Privileged Access Classification
Define what 'privileged' means (roles, groups, high-risk entitlements)
PAM - P3.1 | Define Privileged and Non-Privileged Access Classification Standard | Governance | Sag | Athi | 2026-08-05 | 2026-09-04 | In_Review | In Review per tracker
PAM - P3.2 | Review criteria with infrastructure, Entra, SailPoint, PAM, and application teams | Cross-team | Sag | Sagar | 2026-08-24 | 2026-08-28 | TO DO | Dep: Infra / Entra / SailPoint / PAM / app teams
PAM - P3.3 | Update the standard based on feedback | Governance | Sag | TBD | 2026-08-31 | 2026-09-01 | TO DO
PAM - P3.4 | Obtain formal approval of the classification criteria | Security Governance | Sag | TBD | 2026-09-02 | 2026-09-04 | TO DO
Extract privileged and non-privileged groups/roles/entitlements from AD, Entra, apps
PAM - P3.5 | Extract privileged and non-privileged groups and permissions from AD | Active Directory | Sag | TBD | 2026-09-21 | 2026-09-23 | TO DO
PAM - P3.6 | Extract Entra roles, groups, and assignments | Entra ID | Sag | TBD | 2026-09-24 | 2026-09-28 | TO DO
PAM - P3.7 | Extract SailPoint and Delinea roles and entitlements | SailPoint / Delinea | Sag | TBD | 2026-09-29 | 2026-10-01 | TO DO
PAM - P3.8 | Extract roles and entitlements from applications | Applications | Sag | TBD | 2026-10-02 | 2026-10-08 | TO DO | Dep: app teams
PAM - P3.9 | Normalize and group access objects by platform and application | Inventory | Sag | TBD | 2026-10-09 | 2026-10-13 | TO DO
PAM - P3.10 | Document missing owners, descriptions, and evidence | Inventory | Sag | TBD | 2026-10-14 | 2026-10-16 | TO DO
NEW - Analyze ~21,000 entitlements & bucket into applications (Infrastructure & Cloud team supported)
PAM - P3.10a | Scoping session with Infrastructure & Cloud teams: entitlement sources, extraction owners, access needed | Infra / Cloud | Sag | Infra + Cloud Teams | 2026-10-05 | 2026-10-05 | TO DO | [NEW] Dep: Infra & Cloud team availability - book now
PAM - P3.10b | Submit access / data requests (AD, Entra, Azure RBAC, app databases) | Infra / Cloud | Sag | TBD | 2026-10-06 | 2026-10-06 | TO DO | [NEW] After P3.10a
PAM - P3.10c | Extract entitlements from Azure / cloud resources (RBAC roles, subscriptions, workloads) | Azure / Cloud | Sag | Cloud Team | 2026-10-07 | 2026-10-09 | TO DO | [NEW]
PAM - P3.10d | Define bucketing rules: naming-pattern mapping, group-to-app correlation, catch-all for unknowns | ~21,000 entitlements | Sag | TBD | 2026-10-12 | 2026-10-13 | TO DO | [NEW]
PAM - P3.10e | First-pass automated bucketing (pattern matching, ~60-70% auto-mapped) | ~21,000 entitlements | Sag | TBD | 2026-10-14 | 2026-10-16 | TO DO | [NEW]
PAM - P3.10f | Working sessions with Infra / Cloud SMEs to resolve unmapped entitlements | Infra / Cloud SMEs | Sag | Infra + Cloud Teams | 2026-10-19 | 2026-10-26 | TO DO | [NEW] Dep: SME calendars
PAM - P3.10g | Application-owner validation of entitlement buckets | App owners | Sag | TBD | 2026-10-27 | 2026-11-02 | TO DO | [NEW]
PAM - P3.10h | Publish consolidated entitlement catalog (app-based buckets) | ~21,000 entitlements | Sag | TBD | 2026-11-03 | 2026-11-04 | TO DO | [NEW]
Tag accounts & entitlements privileged vs non-privileged (human & non-human)
PAM - P3.11 | Directory Roles classification | AD / Entra directory roles | Sag | Sagar | 2026-08-10 | 2026-08-28 | In_Progress | Classified into Privileged / Non-Privileged per status report
PAM - P3.12 | Classify AD groups and permissions | Active Directory | Sag | TBD | 2026-12-14 | 2026-12-18 | TO DO | Work in app-criticality order (top 10 first, per P1.21)
PAM - P3.13 | Classify Entra roles, groups, and permissions | Entra ID | Sag | TBD | 2026-12-21 | 2026-12-25 | TO DO
PAM - P3.14 | Classify SailPoint, Delinea, and application entitlements | SailPoint / Delinea / Apps | Sag | TBD | 2026-12-28 | 2027-01-06 | TO DO | Uses entitlement buckets from P3.10h
PAM - P3.15 | Assign privilege tier and sensitive-access categories | All entitlements | Sag | TBD | 2027-01-07 | 2027-01-13 | TO DO
PAM - P3.16 | Map classified access to human and non-human accounts | Inventory | Sag | TBD | 2027-01-14 | 2027-01-20 | TO DO | Dep: P2.33 consolidated inventory
PAM - P3.17 | Record disputed and unclassified items | Inventory | Sag | TBD | 2027-01-21 | 2027-01-22 | TO DO
Build the privileged access register
PAM - P3.18 | Define privileged access register fields | Register | Sag | TBD | 2027-02-08 | 2027-02-08 | TO DO
PAM - P3.19 | Load approved classifications and account assignments | Register | Sag | TBD | 2027-02-09 | 2027-02-11 | TO DO
PAM - P3.20 | Add owners, evidence, rationale, tier, and risk attributes | Register | Sag | TBD | 2027-02-12 | 2027-02-16 | TO DO
PAM - P3.21 | Validate register entries with platform and application owners | Owners | Sag | TBD | 2027-02-17 | 2027-02-22 | TO DO
PAM - P3.22 | Publish the approved privileged access register | Register | Sag | TBD | 2027-02-23 | 2027-02-23 | TO DO
Write the Privileged Access Definition & Standard
PAM - P3.23 | Complete the Privileged Access Definition & Standard | Governance | Sag | TBD | 2027-03-01 | 2027-03-03 | TO DO
PAM - P3.24 | Review the standard with Security Governance and platform teams | Security Governance | Sag | TBD | 2027-03-04 | 2027-03-09 | TO DO
PAM - P3.25 | Update the standard based on comments | Governance | Sag | TBD | 2027-03-10 | 2027-03-11 | TO DO
PAM - P3.26 | Obtain final approval | Security Governance | Sag | TBD | 2027-03-12 | 2027-03-16 | TO DO
PAM - P3.27 | Publish the approved standard | Governance | Sag | TBD | 2027-03-17 | 2027-03-17 | TO DO
Category 4 - Gap Analysis
Reconcile inventory vs SailPoint-managed -> unmanaged accounts gap
PAM - P4.1 | Extract SailPoint-managed account population | SailPoint ISC | Sag | TBD | 2027-01-04 | 2027-01-05 | TO DO
PAM - P4.2 | Match consolidated accounts to SailPoint-managed accounts | SailPoint / Inventory | Sag | TBD | 2027-01-06 | 2027-01-11 | TO DO | Dep: P2.33
PAM - P4.3 | Identify unmanaged and partially governed accounts | SailPoint | Sag | TBD | 2027-01-12 | 2027-01-14 | TO DO
PAM - P4.4 | Validate findings with source owners | Source owners | Sag | TBD | 2027-01-15 | 2027-01-19 | TO DO
PAM - P4.5 | Document SailPoint coverage gaps | Gap Register input | Sag | TBD | 2027-01-20 | 2027-01-21 | TO DO
Reconcile privileged register vs Delinea-vaulted -> unvaulted gap
PAM - P4.6 | Extract Delinea-managed privileged accounts | Delinea | Sag | TBD | 2027-01-25 | 2027-01-26 | TO DO
PAM - P4.7 | Match privileged register against Delinea | Delinea / Register | Sag | TBD | 2027-01-27 | 2027-01-29 | TO DO | Dep: P3.22 register
PAM - P4.8 | Identify unvaulted and partially managed privileged accounts | Delinea | Sag | TBD | 2027-02-01 | 2027-02-03 | TO DO
PAM - P4.9 | Validate PAM applicability with technical owners | Technical owners | Sag | TBD | 2027-02-04 | 2027-02-08 | TO DO
PAM - P4.10 | Document PAM coverage gaps | Gap Register input | Sag | TBD | 2027-02-09 | 2027-02-10 | TO DO
Identify authentication gaps (MFA/CA coverage, legacy auth, SSO)
PAM - P4.11 | Conditional Access Requirement | Entra CA | Sag | TBD | 2027-02-15 | 2027-02-17 | TO DO | Input from P1.27 legacy-auth flags
PAM - P4.12 | Assess MFA and Conditional Access coverage gaps | Entra CA / MFA | Sag | TBD | 2027-02-18 | 2027-02-22 | TO DO | Dep: P2.26-P2.29 MFA data
PAM - P4.13 | Identify legacy authentication and missing SSO | Entra / Apps | Sag | TBD | 2027-02-23 | 2027-02-25 | TO DO
PAM - P4.14 | Identify privileged access without required authentication controls | Privileged accounts | Sag | TBD | 2027-02-26 | 2027-03-02 | TO DO
PAM - P4.15 | Validate exceptions and document recommendations | Gap Register input | Sag | TBD | 2027-03-03 | 2027-03-04 | TO DO
Identify account issues (orphaned, duplicate, terminated-active, stale)
PAM - P4.16 | Identify orphaned and unowned accounts | Inventory | Sag | TBD | 2027-03-08 | 2027-03-10 | TO DO
PAM - P4.17 | Identify duplicate accounts | Inventory | Sag | TBD | 2027-03-11 | 2027-03-12 | TO DO
PAM - P4.18 | Identify terminated identities with active accounts | HR / Inventory | Sag | TBD | 2027-03-15 | 2027-03-17 | TO DO
PAM - P4.19 | Identify stale accounts | Inventory | Sag | TBD | 2027-03-18 | 2027-03-19 | TO DO
PAM - P4.20 | Validate findings and document cleanup recommendations | Gap Register input | Sag | TBD | 2027-03-22 | 2027-03-24 | TO DO
Identify excessive/standing privilege & risky agent permissions
PAM - P4.21 | Identify standing and excessive privileged assignments | Privileged access | Sag | TBD | 2027-03-29 | 2027-03-31 | TO DO
PAM - P4.22 | Identify shared or unowned privileged access | Privileged access | Sag | TBD | 2027-04-01 | 2027-04-05 | TO DO
PAM - P4.23 | Identify risky service, API, bot, and agent permissions | NHI / agents | Sag | TBD | 2027-04-06 | 2027-04-08 | TO DO
PAM - P4.24 | Validate findings with technical and application owners | Owners | Sag | TBD | 2027-04-09 | 2027-04-13 | TO DO
PAM - P4.25 | Document least-privilege and JIT recommendations | Gap Register input | Sag | TBD | 2027-04-14 | 2027-04-15 | TO DO
Consolidate & prioritize into a single Gap Register (risk & criticality)
PAM - P4.26 | Consolidate validated findings into the Gap Register | Gap Register | Sag | TBD | 2027-04-19 | 2027-04-21 | TO DO
PAM - P4.27 | Remove duplicate findings and assign owners | Gap Register | Sag | TBD | 2027-04-22 | 2027-04-26 | TO DO
PAM - P4.28 | Prioritize findings using risk and application criticality | Gap Register | Sag | TBD | 2027-04-27 | 2027-04-29 | TO DO | Uses P1.21 criticality ratings
PAM - P4.29 | Record remediation recommendation and dependency | Gap Register | Sag | TBD | 2027-04-30 | 2027-05-04 | TO DO
PAM - P4.30 | Review and approve the Gap Register | Security Governance | Sag | TBD | 2027-05-05 | 2027-05-07 | TO DO | Closes Roadmap Phase 1 baseline
ROADMAP PHASE 2 - PAM ONBOARDING & SEGMENTATION (Oct 2026 - Nov 2027)
Category 5 - Remediation
Enforce MFA & Conditional Access (staged); disable legacy auth
PAM - P5.11 | Finalize Conditional Access Requirement | Entra CA | Sag | TBD | 2026-10-12 | 2026-10-16 | TO DO | Roadmap Next Milestone: Define CA Policies
PAM - P5.12 | Define pilot population, exclusions, and emergency access handling | Entra CA | Sag | TBD | 2026-10-19 | 2026-10-23 | TO DO
PAM - P5.13 | Test policies in report-only or pilot mode | Entra CA | Sag | TBD | 2026-10-26 | 2026-11-13 | TO DO
PAM - P5.14 | Enforce approved MFA and Conditional Access policies by stage | Entra CA | Sag | TBD | 2026-11-16 | 2026-12-11 | TO DO
PAM - P5.15 | Disable approved legacy authentication methods | Entra / Apps | Sag | TBD | 2026-12-14 | 2026-12-25 | TO DO | Dep: P1.27 legacy-auth list
PAM - P5.16 | Validate enforcement and document exceptions | Entra CA | Sag | TBD | 2026-12-28 | 2027-01-01 | TO DO
Onboard unmanaged accounts into SailPoint
PAM - P5.1 | Confirm approved SailPoint onboarding scope | SailPoint ISC | Sag | TBD | 2027-02-01 | 2027-02-03 | TO DO | Dep: P4.5 coverage gaps
PAM - P5.2 | Configure aggregation and correlation | SailPoint ISC | Sag | TBD | 2027-02-04 | 2027-02-24 | TO DO
PAM - P5.3 | Configure governance and provisioning scope where approved | SailPoint ISC | Sag | TBD | 2027-02-25 | 2027-03-17 | TO DO
PAM - P5.4 | Test onboarding and resolve defects | SailPoint ISC | Sag | TBD | 2027-03-18 | 2027-03-31 | TO DO
PAM - P5.5 | Move approved population into production and close gaps | SailPoint ISC | Sag | TBD | 2027-04-01 | 2027-04-14 | TO DO
Vault privileged accounts into Delinea
PAM - P5.6 | Confirm approved PAM onboarding scope | Delinea | Sag | TBD | 2027-03-01 | 2027-03-03 | TO DO | Dep: P4.10 PAM gaps
PAM - P5.7 | Validate ownership and credential dependencies | Delinea | Sag | TBD | 2027-03-04 | 2027-03-17 | TO DO
PAM - P5.8 | Onboard privileged accounts by platform or application batch | Delinea | Sag | TBD | 2027-03-18 | 2027-05-12 | TO DO
PAM - P5.9 | Configure rotation and approved session controls | Delinea | Sag | TBD | 2027-05-13 | 2027-06-02 | TO DO
PAM - P5.10 | Test PAM controls and update the privileged register | Delinea / Register | Sag | TBD | 2027-06-03 | 2027-06-16 | TO DO
Clean up accounts (disable terminated/orphaned, fix data, resolve duplicates)
PAM - P5.17 | Disable confirmed terminated and orphaned accounts | AD / Entra / Apps | Sag | TBD | 2027-04-05 | 2027-04-16 | TO DO | Dep: P4.20
PAM - P5.18 | Correct account correlation and identity data issues | Inventory | Sag | TBD | 2027-04-19 | 2027-04-30 | TO DO
PAM - P5.19 | Resolve duplicate accounts | AD / Entra / Apps | Sag | TBD | 2027-05-03 | 2027-05-14 | TO DO
PAM - P5.20 | Review and remediate stale accounts | AD / Entra / Apps | Sag | TBD | 2027-05-17 | 2027-05-28 | TO DO
PAM - P5.21 | Update the inventory and document closure evidence | Inventory | Sag | TBD | 2027-05-31 | 2027-06-04 | TO DO
Right-size privileged & agent permissions (least privilege / JIT)
PAM - P5.22 | Remove unnecessary privileged assignments | Privileged access | Sag | TBD | 2027-06-14 | 2027-06-25 | TO DO | Dep: P4.25
PAM - P5.23 | Reduce over-broad roles and split mixed access | Privileged access | Sag | TBD | 2027-06-28 | 2027-07-09 | TO DO
PAM - P5.24 | Convert standing privilege to time-bound access where supported | PIM / Delinea | Sag | TBD | 2027-07-12 | 2027-07-23 | TO DO
PAM - P5.25 | Apply least privilege to service, API, bot, and agent identities | NHI / agents | Sag | TBD | 2027-07-26 | 2027-08-06 | TO DO
PAM - P5.26 | Validate effective access and update the privileged register | Register | Sag | TBD | 2027-08-09 | 2027-08-13 | TO DO
NEW - Separate admin accounts for AD and Entra (admin segmentation)
PAM - P5.26a | Define admin account model: separate account per plane (AD admin / Entra admin / daily-driver), naming, licensing | AD / Entra | Sag | TBD | 2027-05-03 | 2027-05-04 | TO DO | [NEW]
PAM - P5.26b | Inventory current admins holding combined or synced admin access | AD / Entra | Sag | TBD | 2027-05-05 | 2027-05-06 | TO DO | [NEW] Dep: P3.22 privileged register
PAM - P5.26c | Create cloud-only Entra admin accounts (never synced from AD) | Entra ID | Sag | TBD | 2027-05-07 | 2027-05-12 | TO DO | [NEW] Protects Entra plane if AD is compromised
PAM - P5.26d | Create / verify dedicated AD admin accounts (tiered model) | Active Directory | Sag | TBD | 2027-05-13 | 2027-05-18 | TO DO | [NEW]
PAM - P5.26e | Migrate role assignments to new accounts; enforce MFA / CA + PIM on Entra admins | Entra PIM / CA | Sag | TBD | 2027-05-19 | 2027-05-26 | TO DO | [NEW]
PAM - P5.26f | Strip admin rights from old combined accounts; vault new admin credentials in Delinea | AD / Entra / Delinea | Sag | TBD | 2027-05-27 | 2027-06-01 | TO DO | [NEW] Dep: Delinea onboarding (P5.8)
NEW - Create cloud-native Entra groups to replace AD-synced groups
PAM - P5.26g | Identify AD-synced groups used for app assignment, CA targeting, and admin roles | AD / Entra | Sag | TBD | 2027-06-28 | 2027-07-01 | TO DO | [NEW] Synced groups cannot be role-assignable or managed in Entra
PAM - P5.26h | Prioritize groups needing cloud-native equivalents (role-assignable, CA-targeted, PIM-eligible first) | Entra ID | Sag | TBD | 2027-07-02 | 2027-07-05 | TO DO | [NEW]
PAM - P5.26i | Create cloud-native Entra groups and mirror membership | Entra ID | Sag | TBD | 2027-07-06 | 2027-07-09 | TO DO | [NEW]
PAM - P5.26j | Repoint app assignments, CA policies, and role assignments to new groups | Entra ID / Apps | Sag | TBD | 2027-07-12 | 2027-07-19 | TO DO | [NEW] Roadblock: change windows per app
PAM - P5.26k | Deprecate or scope down synced originals; document group source-of-authority rule | AD / Entra | Sag | TBD | 2027-07-20 | 2027-07-21 | TO DO | [NEW]
Convert accounts (unmanaged -> managed, type changes)
PAM - P5.27 | Identify accounts requiring conversion or type correction | Inventory | Sag | TBD | 2027-08-23 | 2027-08-27 | TO DO
PAM - P5.28 | Validate ownership and dependencies | Owners | Sag | TBD | 2027-08-30 | 2027-09-03 | TO DO
PAM - P5.29 | Complete approved account conversions | AD / Entra / SailPoint | Sag | TBD | 2027-09-06 | 2027-09-15 | TO DO
PAM - P5.30 | Test lifecycle and access after conversion | SailPoint | Sag | TBD | 2027-09-16 | 2027-09-21 | TO DO
PAM - P5.31 | Update the consolidated account inventory | Inventory | Sag | TBD | 2027-09-22 | 2027-09-24 | TO DO
Enable / tune Native Change Detection
PAM - P5.32 | Define Native Change Detection scope | SailPoint ISC | Sag | TBD | 2027-09-27 | 2027-09-29 | TO DO
PAM - P5.33 | Configure in-scope sources and attributes | SailPoint ISC | Sag | TBD | 2027-09-30 | 2027-10-06 | TO DO
PAM - P5.34 | Test expected and unauthorized change scenarios | SailPoint ISC | Sag | TBD | 2027-10-07 | 2027-10-13 | TO DO
PAM - P5.35 | Tune alerts and assign response ownership | SailPoint ISC | Sag | TBD | 2027-10-14 | 2027-10-20 | TO DO
PAM - P5.36 | Document and enable recurring monitoring | SailPoint ISC | Sag | TBD | 2027-10-21 | 2027-10-26 | TO DO | Closes Roadmap Phase 2
ROADMAP PHASE 3 - GOVERNANCE & MONITORING (Sep 2026 - Apr 2028)
Category 6 - Access Reviews & Certification
Assess current certification & review coverage vs policy (Existing)
PAM - P6.1 | Collect existing policy, campaign configurations, and results | SailPoint / Policy | Sag | TBD | 2026-11-02 | 2026-11-05 | TO DO
PAM - P6.2 | Map applications and access populations currently reviewed | SailPoint | Sag | TBD | 2026-11-06 | 2026-11-12 | TO DO
PAM - P6.3 | Assess review frequency, reviewers, and completion evidence | SailPoint | Sag | TBD | 2026-11-13 | 2026-11-19 | TO DO
PAM - P6.4 | Identify manual reviews and coverage gaps | SailPoint | Sag | TBD | 2026-11-20 | 2026-11-26 | TO DO
PAM - P6.5 | Validate the current-state assessment | Stakeholders | Sag | TBD | 2026-11-27 | 2026-12-02 | TO DO
Design the review model & campaigns (risk-based)
PAM - P6.6 | Define certification populations and campaign types | SailPoint | Sag | TBD | 2027-01-11 | 2027-01-15 | TO DO
PAM - P6.7 | Define risk-based frequency and reviewer model | SailPoint | Sag | TBD | 2027-01-18 | 2027-01-22 | TO DO | Uses P1.21 app criticality
PAM - P6.8 | Define escalation, evidence, and remediation tracking | SailPoint | Sag | TBD | 2027-01-25 | 2027-01-29 | TO DO
PAM - P6.9 | Design pilot campaign | SailPoint | Sag | TBD | 2027-02-01 | 2027-02-05 | TO DO
PAM - P6.10 | Review and approve the certification model | Security Governance | Sag | TBD | 2027-02-08 | 2027-02-12 | TO DO
Define access outlier logic (peer group, rare entitlements, SoD combos)
PAM - P6.11 | Define peer-group and rare-entitlement logic | SailPoint AI / Analytics | Sag | TBD | 2027-03-01 | 2027-03-05 | TO DO
PAM - P6.12 | Define excessive and dormant-access indicators | SailPoint | Sag | TBD | 2027-03-08 | 2027-03-12 | TO DO
PAM - P6.13 | Define SoD and toxic-combination rules | SailPoint SoD | Sag | TBD | 2027-03-15 | 2027-03-22 | TO DO
PAM - P6.14 | Test logic using sample data | SailPoint | Sag | TBD | 2027-03-23 | 2027-03-30 | TO DO
PAM - P6.15 | Review and approve outlier logic | Security Governance | Sag | TBD | 2027-03-31 | 2027-04-05 | TO DO
Run user certification
PAM - P6.16 | Run user certification | SailPoint campaigns | Sag | TBD | 2027-05-03 | 2027-06-25 | TO DO | Dep: P6.10 model approved
Write the Access Review & Certification Policy
PAM - P6.17 | Draft the Access Review & Certification Policy | Policy | Sag | TBD | 2027-07-05 | 2027-07-09 | TO DO
PAM - P6.18 | Review policy with stakeholders | Stakeholders | Sag | TBD | 2027-07-12 | 2027-07-21 | TO DO
PAM - P6.19 | Update policy based on comments | Policy | Sag | TBD | 2027-07-22 | 2027-07-27 | TO DO
PAM - P6.20 | Obtain formal approval | Security Governance | Sag | TBD | 2027-07-28 | 2027-08-04 | TO DO
PAM - P6.21 | Publish the approved policy | Policy | Sag | TBD | 2027-08-05 | 2027-08-06 | TO DO
Category 7 - JML & Access Processes
Map current JML, access request & provisioning/deprovisioning flows
PAM - P7.1 | Collect current JML process documentation and identify process owners | JML | Sag | TBD | 2027-01-11 | 2027-01-14 | TO DO | [Inferred - verify wording vs v2 file]
PAM - P7.2 | Map joiner, mover, leaver, and contractor lifecycle flows | JML | Sag | TBD | 2027-01-15 | 2027-01-22 | TO DO
PAM - P7.3 | Map access request and approval flow | Access request | Sag | TBD | 2027-01-25 | 2027-01-28 | TO DO
PAM - P7.4 | Map provisioning and deprovisioning flow | SailPoint / target systems | Sag | TBD | 2027-01-29 | 2027-02-04 | TO DO
PAM - P7.5 | Validate current-state maps with process owners | Process owners | Sag | TBD | 2027-02-05 | 2027-02-11 | TO DO
Identify gaps (leaver lag, orphaned, manual steps, missing approvals, SoD)
PAM - P7.6 | Assess joiner, mover, and leaver gaps | JML | Sag | TBD | 2027-02-15 | 2027-02-23 | TO DO
PAM - P7.7 | Identify leaver delays and orphaned-access causes | JML | Sag | TBD | 2027-02-24 | 2027-03-04 | TO DO
PAM - P7.8 | Identify manual steps and missing approvals | JML | Sag | TBD | 2027-03-05 | 2027-03-15 | TO DO
PAM - P7.9 | Identify SoD and failed-fulfillment gaps | SailPoint SoD | Sag | TBD | 2027-03-16 | 2027-03-23 | TO DO
PAM - P7.10 | Prioritize process gaps by risk | JML | Sag | TBD | 2027-03-24 | 2027-03-30 | TO DO
Fix gaps (automate joiner/mover, timely leaver deprovisioning; tighten approvals)
PAM - P7.11 | Approve target-state JML and request design | JML | Sag | TBD | 2027-04-05 | 2027-04-14 | TO DO
PAM - P7.12 | Configure joiner, mover, and leaver improvements | SailPoint workflows | Sag | TBD | 2027-04-15 | 2027-05-12 | TO DO
PAM - P7.13 | Configure approval and SoD improvements | SailPoint | Sag | TBD | 2027-05-13 | 2027-06-02 | TO DO
PAM - P7.14 | Configure exception and failure notifications | SailPoint | Sag | TBD | 2027-06-03 | 2027-06-14 | TO DO
PAM - P7.15 | Test changes and resolve defects | SailPoint | Sag | TBD | 2027-06-15 | 2027-06-30 | TO DO
Validate request -> provision -> deprovision end-to-end
PAM - P7.16 | Define end-to-end test scenarios | JML testing | Sag | TBD | 2027-07-05 | 2027-07-12 | TO DO
PAM - P7.17 | Test request, approval, and provisioning | JML testing | Sag | TBD | 2027-07-13 | 2027-07-28 | TO DO
PAM - P7.18 | Test mover changes and leaver deprovisioning | JML testing | Sag | TBD | 2027-07-29 | 2027-08-13 | TO DO
PAM - P7.19 | Test failure and retry handling | JML testing | Sag | TBD | 2027-08-16 | 2027-08-25 | TO DO
PAM - P7.20 | Document defects, retest, and obtain acceptance | JML testing | Sag | TBD | 2027-08-26 | 2027-09-08 | TO DO
Set up recurring certification campaigns
PAM - P7.21 | Confirm recurring campaign scope and frequency | SailPoint campaigns | Sag | TBD | 2027-09-13 | 2027-09-17 | TO DO
PAM - P7.22 | Confirm reviewer assignments | SailPoint campaigns | Sag | TBD | 2027-09-20 | 2027-09-24 | TO DO
PAM - P7.23 | Configure recurring schedule, reminders, and escalation | SailPoint campaigns | Sag | TBD | 2027-09-27 | 2027-10-06 | TO DO
PAM - P7.24 | Test the recurring campaign | SailPoint campaigns | Sag | TBD | 2027-10-07 | 2027-10-15 | TO DO
PAM - P7.25 | Document ownership and operating procedure | SailPoint campaigns | Sag | TBD | 2027-10-18 | 2027-10-22 | TO DO
Write the Joiner-Mover-Leaver & Access Request Policy
PAM - P7.26 | Draft the JML & Access Request Policy | Policy | Sag | TBD | 2027-10-25 | 2027-10-29 | TO DO
PAM - P7.27 | Review policy with stakeholders | Stakeholders | Sag | TBD | 2027-11-01 | 2027-11-10 | TO DO
PAM - P7.28 | Update policy based on comments | Policy | Sag | TBD | 2027-11-11 | 2027-11-16 | TO DO
PAM - P7.29 | Obtain formal approval | Security Governance | Sag | TBD | 2027-11-17 | 2027-11-24 | TO DO
PAM - P7.30 | Publish the approved policy | Policy | Sag | TBD | 2027-11-25 | 2027-11-26 | TO DO
Category 8 - Policies & Standards
Design & apply Enhanced Managed Access Policies - guideline drafting (near-term per tracker)
PAM - P8.6 | Access Guidelines (SSO/MFA, admin segmentation, admin access requirements) | Guidelines | Sag | TBD | 2026-09-14 | 2026-10-02 | TO DO
PAM - P8.7 | Data Guidelines (DLP, USB, O365) | Guidelines | Sag | TBD | 2026-10-05 | 2026-10-23 | TO DO
PAM - P8.8 | End Point (Intune, risk score, hygiene, naming convention, CIS hardening, etc) | Guidelines | Sag | TBD | 2026-10-26 | 2026-11-13 | TO DO
Consolidate all standards/policies drafted across the program
PAM - P8.1 | Create inventory of current and draft program documents | All program docs | Sag | TBD | 2027-11-01 | 2027-11-05 | TO DO
PAM - P8.2 | Identify duplicate, overlapping, and missing requirements | All program docs | Sag | TBD | 2027-11-08 | 2027-11-15 | TO DO
PAM - P8.3 | Align terminology, roles, exceptions, and review requirements | All program docs | Sag | TBD | 2027-11-16 | 2027-11-23 | TO DO
PAM - P8.4 | Create the consolidated document roadmap | All program docs | Sag | TBD | 2027-11-24 | 2027-11-30 | TO DO
PAM - P8.5 | Review consolidation with document owners | Document owners | Sag | TBD | 2027-12-01 | 2027-12-08 | TO DO
Design & apply Enhanced Managed Access Policies (SoD, birthright, approvals)
PAM - P8.9 | Define SoD, birthright, and approval requirements | Managed access policy | Sag | TBD | 2027-12-13 | 2027-12-24 | TO DO
PAM - P8.10 | Define privileged and sensitive access treatment | Managed access policy | Sag | TBD | 2027-12-27 | 2028-01-07 | TO DO
PAM - P8.11 | Review and apply approved managed-access requirements | SailPoint / Entra | Sag | TBD | 2028-01-10 | 2028-01-25 | TO DO
Review & approval by Security Governance
PAM - P8.12 | Prepare controlled review versions | Governance pack | Sag | TBD | 2028-02-01 | 2028-02-07 | TO DO
PAM - P8.13 | Distribute review pack and track comments | Governance pack | Sag | TBD | 2028-02-08 | 2028-02-15 | TO DO
PAM - P8.14 | Resolve business, technical, risk, and compliance comments | Governance pack | Sag | TBD | 2028-02-16 | 2028-02-25 | TO DO
PAM - P8.15 | Prepare final approval versions | Governance pack | Sag | TBD | 2028-02-28 | 2028-03-02 | TO DO
PAM - P8.16 | Obtain Security Governance approval | Security Governance | Sag | TBD | 2028-03-03 | 2028-03-09 | TO DO
Publish & communicate the policies
PAM - P8.17 | Publish approved documents in the controlled repository | Repository | Sag | TBD | 2028-03-13 | 2028-03-15 | TO DO
PAM - P8.18 | Prepare and deliver stakeholder communications | Comms | Sag | TBD | 2028-03-16 | 2028-03-23 | TO DO
PAM - P8.19 | Update supporting procedures and templates | Procedures | Sag | TBD | 2028-03-24 | 2028-03-31 | TO DO
PAM - P8.20 | Establish exception reporting | Governance | Sag | TBD | 2028-04-03 | 2028-04-07 | TO DO
PAM - P8.21 | Establish periodic review calendar | Governance | Sag | TBD | 2028-04-10 | 2028-04-12 | TO DO | Closes Roadmap Phase 3 / program
Legend:
Completed
In_Progress
In_Review
Blocked
Newly added task (not in v2 plan)
Non-human account focus (carried from v2 highlights)
Editable cells: Responsible User / Execution Owner (currently placeholders), Status, Roadblock/Dependencies. Dates for TO DO items are planned; update Start/End as work begins.