## Secure Access & Priv Control
Cybersecurity Program
Secure Access & Privileged Control - Detailed Project Plan
Timeline: Jun 2026 - Apr 2028 ¦ 3 Roadmap Phases run in parallel, organized into 8 work categories ¦ ~308 working days of effort ¦ Rows in pink = newly added tasks ¦ FINAL v7 - sequential aligned schedule ¦ Gap analysis runs with identification (Phase 1 closes Mar 2027) ¦ Groups before admin accounts ¦ Policy before certification ¦ Open work restarts 8/31/2026 ¦ Updated 8/27/2026
Activity ID | Activity | Scope | Responsible User | Execution Owner | Start Date | End Date | Status | Roadblock/ Dependencies
ROADMAP PHASE 1 - CONDITIONAL ACCESS REVIEW / UPDATE (Jul 2026 - Mar 2027)
Category 1 - Application Inventory & Criticality
Export the full application list from LeanIX
PAM - P1.1 | Export the full application list from LeanIX | LeanIX | Sag | TBD | 2026-07-27 | 2026-08-07 | Completed
Validate completeness (reconcile vs Entra enterprise apps / SSO list)
PAM - P1.2 | Write the Application Criticality & Classification Standard | LeanIX / Governance | Sag | TBD | 2026-07-27 | 2026-09-04 | In_Review | LeanIX review meeting held; final approval pending
PAM - P1.3 | Export Entra enterprise application list | Entra ID | Sag | TBD | 2026-08-31 | 2026-09-01 | TO DO
PAM - P1.4 | Export current SSO application list incl. auth method per app (SAML / OIDC / legacy) | Entra ID / IdP | Sag | LeanIX Team | 2026-09-02 | 2026-09-03 | TO DO | Absorbs former P1.25-P1.28; legacy-auth flags feed CA and P5.11h migration
PAM - P1.5 | Compare LeanIX against Entra enterprise applications | LeanIX / Entra | Sag | TBD | 2026-09-04 | 2026-09-07 | TO DO | After P1.1, P1.3
PAM - P1.6 | Compare LeanIX against SSO application list | LeanIX / IdP | Sag | TBD | 2026-09-08 | 2026-09-09 | TO DO | After P1.4
PAM - P1.7 | Document missing, duplicate, and unmatched applications | LeanIX | Sag | TBD | 2026-09-10 | 2026-09-11 | TO DO
PAM - P1.8 | Review reconciliation exceptions with LeanIX and Entra teams | LeanIX / Entra | Sag | TBD | 2026-09-14 | 2026-09-15 | TO DO | Dep: LeanIX & Entra teams
Define the criticality criteria & scoring scale
PAM - P1.9 | Define business criticality criteria, scoring scale, and thresholds (input to P1.2 Standard) | Governance | Sag | TBD | 2026-08-17 | 2026-08-21 | Completed | Merges former P1.10
PAM - P1.12 | Review and approve the criticality method (approves P1.2 Standard) | Security Governance | Sag | TBD | 2026-08-31 | 2026-09-02 | TO DO
Finalize & send the owner questionnaire (with follow-up/escalation plan)
PAM - P1.13 | Finalize Application Questionnaire (incl. prep - merged former P1.11) | LeanIX Survey | Sag | TBD | 2026-08-17 | 2026-08-21 | Completed | Sent to LeanIX team 8/21
PAM - P1.13a | Package & hand over questionnaire to LeanIX team (format, target list, instructions) | LeanIX team | Sag | TBD | 2026-08-21 | 2026-08-21 | Completed | Handed over 8/21
PAM - P1.15 | Send questionnaire to application owners (distributed by LeanIX team); one-month response window | LeanIX team | Sag | LeanIX Team | 2026-09-01 | 2026-10-01 | TO DO | Distribution 9/1; responses due 10/1
PAM - P1.16 | Track responses and send reminders | LeanIX Survey | Sag | TBD | 2026-09-01 | 2026-10-01 | TO DO | Concurrent with P1.15 response window
PAM - P1.17 | Escalate overdue or incomplete responses | LeanIX Survey | Sag | TBD | 2026-09-24 | 2026-10-08 | TO DO
Score & rank the apps - identify the top 10
PAM - P1.18 | Validate completed questionnaire responses | LeanIX Survey | Sag | TBD | 2026-10-02 | 2026-10-06 | TO DO | After P1.15 window closes 10/1
PAM - P1.19 | Calculate and rank application scores | Scoring model | Sag | TBD | 2026-10-07 | 2026-10-09 | TO DO
PAM - P1.20 | Review scoring exceptions with application owners | App owners | Sag | TBD | 2026-10-12 | 2026-10-15 | TO DO
PAM - P1.21 | Identify and approve the top 10 applications | Security Governance | Sag | TBD | 2026-10-16 | 2026-10-20 | TO DO | Drives classification order, P5.11e/g app priority
Record the criticality ratings back into LeanIX
PAM - P1.24 | Validate criticality ratings loaded into LeanIX (loaded by LeanIX team) | LeanIX | Sag | LeanIX Team | 2026-10-21 | 2026-10-23 | TO DO | Dep: LeanIX team loads ratings after P1.21; absorbs former P1.22/P1.23/P1.24a
Category 2 - Account & Identity Inventory (identification spine)
Pull all accounts (AD, Entra, apps) and HR / Contractor feeds
PAM - P2.1 | Extract of users from each HR | HR systems | Sag | TBD | 2026-08-31 | 2026-09-02 | Blocked | TBD - confirm blocker & owner; restart 8/31
PAM - P2.2 | Extract of users from AD | Active Directory | Sag | Sagar | 2026-07-30 | 2026-08-07 | Completed
PAM - P2.3 | Extract of users from Entra | Entra ID | Sag | Sagar | 2026-07-30 | 2026-08-07 | Completed
PAM - P2.4 | Extract of users from Applications (i.e. EBS) | Applications | Sag | TBD | 2026-09-03 | 2026-09-08 | Blocked | TBD - confirm blocker; dep: app teams
PAM - P2.5 | Extract of contractor record | HR contractor feed | Sag | TBD | 2026-09-09 | 2026-09-11 | TO DO
PAM - P2.6 | Extract of entitlement from AD | Active Directory | Sag | Sagar | 2026-07-30 | 2026-08-07 | Completed
PAM - P2.7 | Extract of entitlement from Entra incl. Azure RBAC (subscriptions, resource groups, workloads) | Entra ID / Azure | Sag | Cloud Team | 2026-07-30 | 2026-09-08 | In_Progress | Entra portion complete 8/7; Azure RBAC portion with Cloud Team (absorbs former P3.10c)
PAM - P2.8 | Extract of entitlement from each Applications (i.e. EBS) | Applications | Sag | TBD | 2026-09-14 | 2026-09-18 | Blocked | TBD - confirm blocker; dep: app teams
Identify human and non-human accounts (incl. servers, API keys)
PAM - P2.9 | Identify human accounts (primary and secondary): tag across AD / Entra / apps incl. SailPoint-managed population, correlate to HR and contractor records, link secondary to primary, resolve exceptions with HR / platform teams | AD / Entra / Apps / HR / SailPoint | Sag | TBD | 2026-09-07 | 2026-10-30 | TO DO | Dep: HR & platform teams; merges former P2.10-P2.17 + P4.1-P4.2
PAM - P2.9a | Identify non-human accounts (service accounts, admin accounts, API / bot / workload identities) | AD / Entra / Apps | Sag | TBD | 2026-09-07 | 2026-09-18 | TO DO | Feeds P2.18 classification; vaulting via P5.8 Wave 1
PAM - P2.9b | Identify servers and local privileged accounts (Windows local admins, Linux root / sudo, appliance built-ins) | Servers / CMDB | Sag | Infra Team | 2026-09-21 | 2026-10-09 | TO DO | Dep: Infra team + ServiceNow CMDB inventory; vaulting via P5.8c
PAM - P2.9c | Identify API keys, secrets, and static credentials (app configs, integrations, cloud key stores, CI/CD pipelines) | Apps / Cloud | Sag | Cloud Team | 2026-09-21 | 2026-10-30 | TO DO | Dep: app teams + Cloud team; discovery tooling may be needed; vaulting via P5.8d
Classify non-human accounts, assign owners & map dependencies
PAM - P2.18 | Classify non-human accounts (service, shared, API, bot, workload), assign business / technical owners for each identified account, escalate unowned, and map dependencies (consuming systems / apps, integrations, jobs, credential dependencies) validated with technical owners | NHI / Inventory | Sag | TBD | 2026-10-12 | 2026-11-19 | TO DO | Dep: technical owners; merges former P2.19-P2.25
PAM - P2.21a | Data analysis: assess impact of processing identified accounts through SailPoint (correlation keys, source readiness, lifecycle behavior, provisioning risk) | SailPoint / Inventory | Sag | TBD | 2026-11-20 | 2026-11-27 | TO DO | Readiness gate for P5.5a / P5.8 Wave 1
Category 3 - Privileged Access Classification
Define what 'privileged' means (roles, groups, high-risk entitlements)
PAM - P3.1 | Define Privileged and Non-Privileged Access Classification Standard | Governance | Sag | Athi | 2026-08-05 | 2026-08-21 | Completed | Same document as P3.23; former P3.2-P3.4 superseded by P3.24-P3.27 review chain
Consolidate extracts & candidate identification
PAM - P3.5 | Consolidate extracts (AD, Entra incl. Azure RBAC, apps, SailPoint / Delinea) and identify privileged vs non-privileged candidate objects | All platforms | Sag | TBD | 2026-09-16 | 2026-09-24 | TO DO | Merges former P3.5-P3.8; raw extraction owned by P2.6-P2.8; feeds P3.10d bucketing
PAM - P3.10 | Document missing owners, descriptions, and evidence | Inventory | Sag | TBD | 2026-09-25 | 2026-09-30 | TO DO
Analyze ~21,000 entitlements & bucket into applications (Infrastructure & Cloud supported)
PAM - P3.10a | Scoping session with Infrastructure & Cloud teams: entitlement sources, extraction owners, access needed (access / data requests agreed in-session) | Infra / Cloud | Sag | Infra + Cloud Teams | 2026-10-05 | 2026-10-05 | TO DO | Dep: Infra & Cloud availability; absorbs former P3.10b
PAM - P3.10d | Define bucketing criteria | ~21,000 entitlements | Sag | TBD | 2026-10-06 | 2026-10-08 | TO DO | Naming-pattern mapping, group-to-app correlation, catch-all for unknowns
PAM - P3.10f | Working sessions with Infra / Cloud SMEs to resolve unmapped entitlements after criteria applied | Infra / Cloud SMEs | Sag | Infra + Cloud Teams | 2026-10-09 | 2026-10-23 | TO DO | Dep: SME calendars; absorbs first-pass application (former P3.10e)
PAM - P3.10g | Application-owner validation of entitlement buckets | App owners | Sag | TBD | 2026-10-26 | 2026-11-03 | TO DO
PAM - P3.10h | Publish consolidated entitlement catalog (app-based buckets) | ~21,000 entitlements | Sag | TBD | 2026-11-04 | 2026-11-06 | TO DO
Tag accounts & entitlements privileged vs non-privileged (human & non-human)
PAM - P3.11 | Directory Roles classification | AD / Entra directory roles | Sag | Sagar | 2026-08-10 | 2026-08-21 | Completed | Reported complete in status update
PAM - P3.12 | Classify AD groups and permissions | Active Directory | Sag | TBD | 2026-11-09 | 2026-11-16 | TO DO | App-criticality order (top 10 first, per P1.21)
PAM - P3.13 | Classify Entra roles, groups, and permissions | Entra ID | Sag | TBD | 2026-11-17 | 2026-11-24 | TO DO
PAM - P3.14 | Classify SailPoint, Delinea, and application entitlements | SailPoint / Delinea / Apps | Sag | TBD | 2026-11-25 | 2026-12-07 | TO DO | Uses P3.10h entitlement buckets
PAM - P3.15 | Assign privilege tier and sensitive-access categories | All entitlements | Sag | TBD | 2026-12-08 | 2026-12-15 | TO DO
PAM - P3.16 | Map classified access to human and non-human accounts | Inventory | Sag | TBD | 2026-12-16 | 2026-12-23 | TO DO | Uses P2.9 / P2.9a-c identification working data
PAM - P3.17 | Record disputed and unclassified items | Inventory | Sag | TBD | 2026-12-24 | 2026-12-28 | TO DO
Build the privileged access register
PAM - P3.18 | Define privileged access register fields | Register | Sag | TBD | 2027-01-04 | 2027-01-05 | TO DO
PAM - P3.19 | Load approved classifications and account assignments | Register | Sag | TBD | 2027-01-06 | 2027-01-08 | TO DO
PAM - P3.20 | Add owners, evidence, rationale, tier, and risk attributes | Register | Sag | TBD | 2027-01-11 | 2027-01-14 | TO DO
PAM - P3.21 | Validate register entries with platform and application owners | Owners | Sag | TBD | 2027-01-15 | 2027-01-21 | TO DO
PAM - P3.22 | Publish the approved privileged access register | Register | Sag | TBD | 2027-01-22 | 2027-01-25 | TO DO | Feeds P4.7 Delinea true-up + P5.8 Wave 1
Write the Privileged Access Definition & Standard
PAM - P3.23 | Complete the Privileged Access Definition & Standard | Governance | Sag | TBD | 2026-08-05 | 2026-08-21 | Completed
PAM - P3.24 | Review the standard with Security Governance and platform teams | Security Governance | Sag | TBD | 2026-08-31 | 2026-09-04 | TO DO
PAM - P3.25 | Update the standard based on comments | Governance | Sag | TBD | 2026-09-07 | 2026-09-09 | TO DO
PAM - P3.26 | Obtain final approval | Security Governance | Sag | TBD | 2026-09-10 | 2026-09-15 | TO DO
PAM - P3.27 | Publish the approved standard | Governance | Sag | TBD | 2026-09-16 | 2026-09-17 | TO DO
Category 4 - Gap Analysis (runs concurrently with identification)
Identify gaps during identification (SailPoint coverage, account issues, PAM, auth, standing privilege)
PAM - P4.3 | Identify unmanaged and partially governed accounts | SailPoint | Sag | TBD | 2026-10-19 | 2026-10-22 | TO DO | From P2.9 SailPoint reconciliation (former P4.1-P4.2 merged into P2.9)
PAM - P4.4 | Validate findings with source owners | Source owners | Sag | TBD | 2026-10-23 | 2026-10-28 | TO DO
PAM - P4.5 | Document SailPoint coverage gaps | Gap Register input | Sag | TBD | 2026-10-29 | 2026-11-02 | TO DO | Feeds P5.1 onboarding scope
PAM - P4.16 | Identify orphaned and unowned accounts | Inventory | Sag | TBD | 2026-11-03 | 2026-11-06 | TO DO
PAM - P4.17 | Identify duplicate accounts | Inventory | Sag | TBD | 2026-11-09 | 2026-11-11 | TO DO
PAM - P4.18 | Identify terminated identities with active accounts | HR / Inventory | Sag | TBD | 2026-11-12 | 2026-11-17 | TO DO
PAM - P4.19 | Identify stale accounts | Inventory | Sag | TBD | 2026-11-18 | 2026-11-20 | TO DO
PAM - P4.20 | Validate findings and document cleanup recommendations | Gap Register input | Sag | TBD | 2026-11-23 | 2026-11-26 | TO DO | Feeds P5.17 rolling cleanup
PAM - P4.6 | Extract Delinea-managed privileged accounts | Delinea | Sag | TBD | 2026-11-27 | 2026-12-01 | TO DO
PAM - P4.7 | Match privileged register against Delinea | Delinea / Register | Sag | TBD | 2026-12-02 | 2026-12-07 | TO DO | Against P2.9a working data; true-up after P3.22 publishes
PAM - P4.8 | Identify unvaulted and partially managed privileged accounts | Delinea | Sag | TBD | 2026-12-08 | 2026-12-11 | TO DO
PAM - P4.9 | Validate PAM applicability with technical owners | Technical owners | Sag | TBD | 2026-12-14 | 2026-12-17 | TO DO
PAM - P4.10 | Document PAM coverage gaps | Gap Register input | Sag | TBD | 2026-12-18 | 2026-12-22 | TO DO | Feeds P5.6 PAM scope
PAM - P4.11 | Document Conditional Access requirement gaps (input to P5.11 policy definition) | Entra CA | Sag | TBD | 2026-12-23 | 2026-12-28 | TO DO | Input from P1.4 auth data (former P4.13 merged)
PAM - P4.12 | Assess MFA and Conditional Access coverage gaps | Entra CA / MFA | Sag | TBD | 2026-12-29 | 2027-01-01 | TO DO
PAM - P4.14 | Identify privileged access without required authentication controls | Privileged accounts | Sag | TBD | 2027-01-04 | 2027-01-07 | TO DO
PAM - P4.15 | Validate exceptions and document recommendations | Gap Register input | Sag | TBD | 2027-01-08 | 2027-01-12 | TO DO
PAM - P4.21 | Identify standing and excessive privileged assignments | Privileged access | Sag | TBD | 2027-01-13 | 2027-01-18 | TO DO
PAM - P4.22 | Identify shared or unowned privileged access | Privileged access | Sag | TBD | 2027-01-19 | 2027-01-22 | TO DO
PAM - P4.23 | Identify risky service, API, bot, and agent permissions | NHI / agents | Sag | TBD | 2027-01-25 | 2027-01-28 | TO DO
PAM - P4.24 | Validate findings with technical and application owners | Owners | Sag | TBD | 2027-01-29 | 2027-02-03 | TO DO
PAM - P4.25 | Document least-privilege and JIT recommendations | Gap Register input | Sag | TBD | 2027-02-04 | 2027-02-08 | TO DO
Consolidate & prioritize into a single Gap Register (risk & criticality)
PAM - P4.26 | Consolidate validated findings into the Gap Register | Gap Register | Sag | TBD | 2027-02-11 | 2027-02-16 | TO DO
PAM - P4.27 | Remove duplicate findings and assign owners | Gap Register | Sag | TBD | 2027-02-17 | 2027-02-22 | TO DO
PAM - P4.28 | Prioritize findings using risk and application criticality | Gap Register | Sag | TBD | 2027-02-23 | 2027-02-26 | TO DO | Uses P1.21 criticality ratings
PAM - P4.29 | Record remediation recommendation and dependency | Gap Register | Sag | TBD | 2027-03-01 | 2027-03-04 | TO DO
PAM - P4.30 | Review and approve the Gap Register | Security Governance | Sag | TBD | 2027-03-05 | 2027-03-10 | TO DO | Closes Roadmap Phase 1 baseline (~Mar 2027)
ROADMAP PHASE 2 - PAM ONBOARDING & SEGMENTATION (Sep 2026 - Sep 2027)
Category 8 (early) - Guideline Drafting (Access / Data / Endpoint)
Design & apply Enhanced Managed Access Policies - guideline drafting (near-term per tracker)
PAM - P8.6 | Access Guidelines (SSO/MFA, admin segmentation, admin access requirements) | Guidelines | Sag | TBD | 2026-09-14 | 2026-10-02 | TO DO
PAM - P8.7 | Data Guidelines (DLP, USB, O365) | Guidelines | Sag | TBD | 2026-10-05 | 2026-10-23 | TO DO
PAM - P8.8 | End Point (Intune, risk score, hygiene, naming convention, CIS hardening, etc) | Guidelines | Sag | TBD | 2026-10-26 | 2026-11-13 | TO DO
Category 5 - Remediation
Application onboarding & SSO integration via Entra (Entra team dependency)
PAM - P5.11a | Define application onboarding standard: SSO required (SAML/OIDC), group-based assignment, naming, ownership | Entra ID | Sag | TBD | 2026-10-01 | 2026-10-05 | TO DO
PAM - P5.11b | Set up intake / request process with Entra team (who creates groups, who configures connections, SLA) | Entra team | Sag | Entra Team | 2026-10-06 | 2026-10-07 | TO DO | Dep: Entra team agreement
PAM - P5.11c | Entra team: create assignment groups per app (cloud-native) | Entra ID | Sag | Entra Team | 2026-10-08 | 2026-10-21 | TO DO | HARD DEPENDENCY - app assignment blocked without these; same group standard as P5.26g-i
PAM - P5.11d | Entra team: register enterprise apps & configure SSO connections (SAML/OIDC) | Entra ID | Sag | Entra Team | 2026-10-22 | 2026-11-11 | TO DO | Dep: Entra team; per app batch
PAM - P5.11e | Consult risky application owners: birthright access to apply per app (attribute-based auto-assignment at joiner) | App owners | Sag | App Owners | 2026-11-12 | 2026-11-18 | TO DO | Risk / criticality list from P1.21; feeds P8.9
PAM - P5.11f | Configure approved birthright assignments (Entra dynamic groups / SailPoint birthright roles) | Entra / SailPoint | Sag | TBD | 2026-11-19 | 2026-11-30 | TO DO | After P5.11e owner sign-off
PAM - P5.11g | Onboard critical apps end-to-end (group -> connection -> assignment -> birthright -> CA applied) | Entra ID / Apps | Sag | TBD | 2026-12-01 | 2026-12-21 | TO DO | Priority order from P1.21 top-10 approval
PAM - P5.11h | Migrate legacy-auth apps to Entra SSO in batches (list from P1.4) | Entra ID / Apps | Sag | TBD | 2026-12-22 | 2027-03-15 | TO DO | Must precede per-app legacy-auth disable (P5.15)
PAM - P5.11i | Verify CA policies apply to each onboarded app | Entra CA | Sag | TBD | 2027-03-16 | 2027-03-29 | TO DO
Enforce MFA & Conditional Access (staged); disable legacy auth
PAM - P5.11 | Finalize Conditional Access Requirement | Entra CA | Sag | TBD | 2026-10-12 | 2026-10-16 | TO DO | Roadmap Next Milestone: Define CA Policies
PAM - P5.12 | Define pilot population, exclusions, and emergency access handling | Entra CA | Sag | TBD | 2026-10-19 | 2026-10-23 | TO DO
PAM - P5.13 | Test policies in report-only or pilot mode | Entra CA | Sag | TBD | 2026-10-26 | 2026-11-13 | TO DO
PAM - P5.14 | Enforce approved MFA and Conditional Access policies by stage | Entra CA | Sag | TBD | 2026-11-16 | 2026-12-14 | TO DO
PAM - P5.15 | Disable approved legacy authentication methods (per app, only after its P5.11h SSO migration) | Entra / Apps | Sag | TBD | 2027-01-04 | 2027-03-26 | TO DO | Dep: P5.11h migration per app; list from P1.4
PAM - P5.16 | Validate enforcement and document exceptions | Entra CA | Sag | TBD | 2027-03-29 | 2027-04-02 | TO DO
Onboard unmanaged accounts into SailPoint
PAM - P5.1 | Confirm approved SailPoint onboarding scope | SailPoint ISC | Sag | TBD | 2026-11-09 | 2026-11-11 | TO DO | Dep: P4.5 coverage gaps
PAM - P5.2 | SailPoint provisioning development (aggregation & correlation, governance and provisioning scope, onboarding testing & defect resolution) | SailPoint ISC | Sag | TBD | 2026-11-12 | 2026-12-30 | TO DO | Merges former P5.2-P5.4
PAM - P5.5 | Move approved population into production and close gaps | SailPoint ISC | Sag | TBD | 2026-12-31 | 2027-01-13 | TO DO
PAM - P5.5a | Provision and govern service accounts through SailPoint (source onboarding, ownership assignment, lifecycle policy) | SailPoint ISC | Sag | TBD | 2027-01-14 | 2027-02-17 | TO DO | Dep: P2.21a impact analysis + P2.18 owners
PAM onboarding into Delinea - two waves
PAM - P5.6 | Confirm approved PAM onboarding scope | Delinea | Sag | TBD | 2027-01-04 | 2027-01-06 | TO DO | Dep: P4.10 PAM gaps
PAM - P5.7 | Validate ownership and credential dependencies | Delinea | Sag | TBD | 2027-01-07 | 2027-01-20 | TO DO
PAM - P5.8 | PAM onboarding Wave 1: vault existing identified accounts (privileged, admin, service) by platform / application batch | Delinea | Sag | TBD | 2027-01-21 | 2027-03-17 | TO DO | Dep: P2.9/P2.9a identification + P2.18 classification + P3.22 register
PAM - P5.8a | Onboard identified service & admin accounts (from Category 2 inventory) into Delinea vaulting | Delinea | Sag | TBD | 2027-03-18 | 2027-04-07 | TO DO | Wave 1 detail; dep: P2.9a + P2.18 owners
PAM - P5.8c | Vault server local privileged accounts into Delinea with rotation (per server batch) | Delinea / Servers | Sag | TBD | 2027-04-08 | 2027-05-05 | TO DO | Dep: P2.9b server inventory + P2.18 owners
PAM - P5.8d | Vault API keys & secrets into Delinea; rotate and remediate insecurely stored credentials (configs, scripts, pipelines) | Delinea / Apps / Cloud | Sag | TBD | 2027-05-06 | 2027-06-16 | TO DO | Dep: P2.9c inventory + app-owner coordination per consumer
PAM - P5.9 | Configure rotation and approved session controls | Delinea | Sag | TBD | 2027-06-17 | 2027-07-07 | TO DO
PAM - P5.10 | Test PAM controls and update the privileged register | Delinea / Register | Sag | TBD | 2027-07-08 | 2027-07-21 | TO DO
PAM - P5.8b | PAM onboarding Wave 2: vault accounts from newly onboarded HR sources (recurring - new joiners / privileged accounts as sources feed SailPoint) | Delinea | Sag | TBD | 2027-07-01 | 2027-09-30 | TO DO | Dep: P5.2 SailPoint provisioning + P7.12 JML; recurring / BAU transition
Clean up accounts - rolling with identification
PAM - P5.17 | Clean up accounts as identified: disable confirmed terminated / orphaned, correct correlation & identity data issues, resolve duplicates, remediate stale accounts, document closure evidence | AD / Entra / Apps / Inventory | Sag | TBD | 2026-11-09 | 2027-02-26 | TO DO | Rolling, per validated finding batches (P4.16-P4.20); merges former P5.18-P5.21
Convert accounts (unmanaged -> managed, type changes) - post-identification
PAM - P5.27 | Identify accounts requiring conversion or type correction | Inventory | Sag | TBD | 2027-02-01 | 2027-02-05 | TO DO | Dep: P2.9/P2.9a identification + validated findings
PAM - P5.28 | Validate ownership and dependencies | Owners | Sag | TBD | 2027-02-08 | 2027-02-12 | TO DO
PAM - P5.29 | Complete approved account conversions | AD / Entra / SailPoint | Sag | TBD | 2027-02-15 | 2027-02-25 | TO DO
PAM - P5.30 | Test lifecycle and access after conversion | SailPoint | Sag | TBD | 2027-02-26 | 2027-03-04 | TO DO
PAM - P5.31 | Update the consolidated account inventory | Inventory | Sag | TBD | 2027-03-05 | 2027-03-09 | TO DO
Create cloud-native Entra groups to replace AD-synced groups (FIRST - scaffolding for admin accounts)
PAM - P5.26g | Identify AD-synced groups used for app assignment, CA targeting, and admin roles | AD / Entra | Sag | TBD | 2027-02-01 | 2027-02-05 | TO DO | Synced groups cannot be role-assignable or managed in Entra
PAM - P5.26h | Prioritize groups needing cloud-native equivalents (role-assignable, CA-targeted, PIM-eligible first) | Entra ID | Sag | TBD | 2027-02-08 | 2027-02-10 | TO DO
PAM - P5.26i | Create cloud-native Entra groups and mirror membership | Entra ID | Sag | TBD | 2027-02-11 | 2027-02-17 | TO DO
PAM - P5.26j | Repoint app assignments, CA policies, and role assignments to new groups | Entra ID / Apps | Sag | TBD | 2027-02-18 | 2027-03-03 | TO DO | Roadblock: change windows per app
PAM - P5.26k | Deprecate or scope down synced originals; document group source-of-authority rule | AD / Entra | Sag | TBD | 2027-03-04 | 2027-03-08 | TO DO
Separate admin accounts for AD and Entra (AFTER groups exist)
PAM - P5.26a | Define admin account model: separate account per plane (AD admin / Entra admin / daily-driver), naming, licensing | AD / Entra | Sag | TBD | 2027-03-09 | 2027-03-11 | TO DO
PAM - P5.26b | Inventory current admins holding combined or synced admin access | AD / Entra | Sag | TBD | 2027-03-12 | 2027-03-16 | TO DO | Dep: P3.22 privileged register
PAM - P5.26c | Create cloud-only Entra admin accounts (never synced from AD) | Entra ID | Sag | TBD | 2027-03-17 | 2027-03-23 | TO DO
PAM - P5.26d | Create / verify dedicated AD admin accounts (tiered model) | Active Directory | Sag | TBD | 2027-03-24 | 2027-03-30 | TO DO
PAM - P5.26e | Migrate role assignments to new accounts via cloud-native groups; enforce MFA / CA + PIM on Entra admins | Entra PIM / CA | Sag | TBD | 2027-03-31 | 2027-04-09 | TO DO | Dep: P5.26i-j groups live
PAM - P5.26f | Strip admin rights from old combined accounts; vault new admin credentials in Delinea | AD / Entra / Delinea | Sag | TBD | 2027-04-12 | 2027-04-16 | TO DO | Dep: P5.8 Wave 1
Enable / tune Native Change Detection
PAM - P5.32 | Define Native Change Detection scope | SailPoint ISC | Sag | TBD | 2027-08-02 | 2027-08-04 | TO DO
PAM - P5.33 | Configure in-scope sources and attributes | SailPoint ISC | Sag | TBD | 2027-08-05 | 2027-08-11 | TO DO
PAM - P5.34 | Test expected and unauthorized change scenarios | SailPoint ISC | Sag | TBD | 2027-08-12 | 2027-08-18 | TO DO
PAM - P5.35 | Tune alerts and assign response ownership | SailPoint ISC | Sag | TBD | 2027-08-19 | 2027-08-25 | TO DO
PAM - P5.36 | Document and enable recurring monitoring | SailPoint ISC | Sag | TBD | 2027-08-26 | 2027-09-01 | TO DO | Closes Roadmap Phase 2
ROADMAP PHASE 3 - GOVERNANCE & MONITORING (Nov 2026 - Apr 2028)
Category 2 (reporting) - Consolidated Account Inventory
Consolidated inventory reporting (moved from Category 2 per decision)
PAM - P2.30 | Produce and publish the consolidated account inventory report (normalize / merge HR, AD, Entra, app extracts; add classification, correlation, ownership, dependency, MFA data; data-quality review) | Inventory / Reporting | Sag | TBD | 2026-12-01 | 2026-12-18 | TO DO | Merges former P2.31-P2.33; reporting deliverable - gap analysis consumes working data directly
Category 6 - Access Reviews & Certification
Assess current certification & review coverage vs policy (Existing)
PAM - P6.1 | Collect existing policy, campaign configurations, and results | SailPoint / Policy | Sag | TBD | 2026-11-02 | 2026-11-06 | TO DO
PAM - P6.2 | Map applications and access populations currently reviewed | SailPoint | Sag | TBD | 2026-11-09 | 2026-11-13 | TO DO
PAM - P6.3 | Assess review frequency, reviewers, and completion evidence | SailPoint | Sag | TBD | 2026-11-16 | 2026-11-20 | TO DO
PAM - P6.4 | Identify manual reviews and coverage gaps | SailPoint | Sag | TBD | 2026-11-23 | 2026-11-27 | TO DO
PAM - P6.5 | Validate the current-state assessment | Stakeholders | Sag | TBD | 2026-11-30 | 2026-12-04 | TO DO
Design the review model & campaigns (risk-based)
PAM - P6.6 | Define certification populations and campaign types | SailPoint | Sag | TBD | 2027-01-11 | 2027-01-15 | TO DO
PAM - P6.7 | Define risk-based frequency and reviewer model | SailPoint | Sag | TBD | 2027-01-18 | 2027-01-22 | TO DO | Uses P1.21 app criticality
PAM - P6.8 | Define escalation, evidence, and remediation tracking | SailPoint | Sag | TBD | 2027-01-25 | 2027-01-29 | TO DO
PAM - P6.9 | Design pilot campaign | SailPoint | Sag | TBD | 2027-02-01 | 2027-02-05 | TO DO
PAM - P6.10 | Review and approve the certification model | Security Governance | Sag | TBD | 2027-02-08 | 2027-02-12 | TO DO
Write the Access Review & Certification Policy (BEFORE certification run)
PAM - P6.17 | Draft the Access Review & Certification Policy | Policy | Sag | TBD | 2027-02-15 | 2027-02-19 | TO DO
PAM - P6.18 | Review policy with stakeholders | Stakeholders | Sag | TBD | 2027-02-22 | 2027-03-02 | TO DO
PAM - P6.19 | Update policy based on comments | Policy | Sag | TBD | 2027-03-03 | 2027-03-08 | TO DO
PAM - P6.20 | Obtain formal approval | Security Governance | Sag | TBD | 2027-03-09 | 2027-03-16 | TO DO
PAM - P6.21 | Publish the approved policy | Policy | Sag | TBD | 2027-03-17 | 2027-03-18 | TO DO | Prerequisite for P6.16 certification run
Define access outlier logic (peer group, rare entitlements, SoD combos)
PAM - P6.11 | Define peer-group and rare-entitlement logic | SailPoint AI / Analytics | Sag | TBD | 2027-03-19 | 2027-03-25 | TO DO
PAM - P6.12 | Define excessive and dormant-access indicators | SailPoint | Sag | TBD | 2027-03-26 | 2027-04-01 | TO DO
PAM - P6.13 | Define SoD and toxic-combination rules | SailPoint SoD | Sag | TBD | 2027-04-02 | 2027-04-09 | TO DO
PAM - P6.14 | Test logic using sample data | SailPoint | Sag | TBD | 2027-04-12 | 2027-04-19 | TO DO
PAM - P6.15 | Review and approve outlier logic | Security Governance | Sag | TBD | 2027-04-20 | 2027-04-23 | TO DO
Run user certification
PAM - P6.16 | Run user certification | SailPoint campaigns | Sag | TBD | 2027-05-03 | 2027-06-25 | TO DO | Dep: P6.21 published policy + P6.10 approved model; SailPoint-automated
Category 7 - JML & Access Processes
Map current JML, access request & provisioning/deprovisioning flows
PAM - P7.1 | Collect current JML process documentation and identify process owners | JML | Sag | TBD | 2027-01-11 | 2027-01-14 | TO DO | [Inferred wording - verify vs master]
PAM - P7.2 | Map joiner, mover, leaver, and contractor lifecycle flows | JML | Sag | TBD | 2027-01-15 | 2027-01-22 | TO DO
PAM - P7.3 | Map access request and approval flow | Access request | Sag | TBD | 2027-01-25 | 2027-01-28 | TO DO
PAM - P7.4 | Map provisioning and deprovisioning flow | SailPoint / target systems | Sag | TBD | 2027-01-29 | 2027-02-04 | TO DO
PAM - P7.5 | Validate current-state maps with process owners | Process owners | Sag | TBD | 2027-02-05 | 2027-02-11 | TO DO
Identify gaps (leaver lag, orphaned, manual steps, missing approvals, SoD)
PAM - P7.6 | Assess joiner, mover, and leaver gaps | JML | Sag | TBD | 2027-02-15 | 2027-02-23 | TO DO
PAM - P7.7 | Identify leaver delays and orphaned-access causes | JML | Sag | TBD | 2027-02-24 | 2027-03-04 | TO DO
PAM - P7.8 | Identify manual steps and missing approvals | JML | Sag | TBD | 2027-03-05 | 2027-03-15 | TO DO
PAM - P7.9 | Identify SoD and failed-fulfillment gaps | SailPoint SoD | Sag | TBD | 2027-03-16 | 2027-03-23 | TO DO
PAM - P7.10 | Prioritize process gaps by risk | JML | Sag | TBD | 2027-03-24 | 2027-03-30 | TO DO
Fix gaps (automate joiner/mover, timely leaver deprovisioning; tighten approvals)
PAM - P7.11 | Approve target-state JML and request design | JML | Sag | TBD | 2027-04-05 | 2027-04-14 | TO DO
PAM - P7.12 | Configure joiner, mover, and leaver improvements | SailPoint workflows | Sag | TBD | 2027-04-15 | 2027-05-12 | TO DO | Feeds P5.8b Wave 2
PAM - P7.13 | Configure approval and SoD improvements | SailPoint | Sag | TBD | 2027-05-13 | 2027-06-02 | TO DO
PAM - P7.14 | Configure exception and failure notifications | SailPoint | Sag | TBD | 2027-06-03 | 2027-06-14 | TO DO
PAM - P7.15 | Test changes and resolve defects | SailPoint | Sag | TBD | 2027-06-15 | 2027-06-30 | TO DO
Validate request -> provision -> deprovision end-to-end
PAM - P7.16 | Define end-to-end test scenarios | JML testing | Sag | TBD | 2027-07-05 | 2027-07-12 | TO DO
PAM - P7.17 | Test request, approval, and provisioning | JML testing | Sag | TBD | 2027-07-13 | 2027-07-28 | TO DO
PAM - P7.18 | Test mover changes and leaver deprovisioning | JML testing | Sag | TBD | 2027-07-29 | 2027-08-13 | TO DO
PAM - P7.19 | Test failure and retry handling | JML testing | Sag | TBD | 2027-08-16 | 2027-08-25 | TO DO
PAM - P7.20 | Document defects, retest, and obtain acceptance | JML testing | Sag | TBD | 2027-08-26 | 2027-09-08 | TO DO
Set up recurring certification campaigns
PAM - P7.21 | Confirm recurring campaign scope and frequency | SailPoint campaigns | Sag | TBD | 2027-09-13 | 2027-09-17 | TO DO
PAM - P7.22 | Confirm reviewer assignments | SailPoint campaigns | Sag | TBD | 2027-09-20 | 2027-09-24 | TO DO
PAM - P7.23 | Configure recurring schedule, reminders, and escalation | SailPoint campaigns | Sag | TBD | 2027-09-27 | 2027-10-06 | TO DO
PAM - P7.24 | Test the recurring campaign | SailPoint campaigns | Sag | TBD | 2027-10-07 | 2027-10-15 | TO DO
PAM - P7.25 | Document ownership and operating procedure | SailPoint campaigns | Sag | TBD | 2027-10-18 | 2027-10-22 | TO DO
Write the Joiner-Mover-Leaver & Access Request Policy
PAM - P7.26 | Draft the JML & Access Request Policy | Policy | Sag | TBD | 2027-10-25 | 2027-10-29 | TO DO
PAM - P7.27 | Review policy with stakeholders | Stakeholders | Sag | TBD | 2027-11-01 | 2027-11-10 | TO DO
PAM - P7.28 | Update policy based on comments | Policy | Sag | TBD | 2027-11-11 | 2027-11-16 | TO DO
PAM - P7.29 | Obtain formal approval | Security Governance | Sag | TBD | 2027-11-17 | 2027-11-24 | TO DO
PAM - P7.30 | Publish the approved policy | Policy | Sag | TBD | 2027-11-25 | 2027-11-26 | TO DO
Category 8 - Policies & Standards
Consolidate all standards/policies drafted across the program
PAM - P8.1 | Create inventory of current and draft program documents | All program docs | Sag | TBD | 2027-11-01 | 2027-11-05 | TO DO
PAM - P8.2 | Identify duplicate, overlapping, and missing requirements | All program docs | Sag | TBD | 2027-11-08 | 2027-11-15 | TO DO
PAM - P8.3 | Align terminology, roles, exceptions, and review requirements | All program docs | Sag | TBD | 2027-11-16 | 2027-11-23 | TO DO
PAM - P8.4 | Create the consolidated document roadmap | All program docs | Sag | TBD | 2027-11-24 | 2027-11-30 | TO DO
PAM - P8.5 | Review consolidation with document owners | Document owners | Sag | TBD | 2027-12-01 | 2027-12-08 | TO DO
Design & apply Enhanced Managed Access Policies (SoD, birthright, approvals)
PAM - P8.9 | Define SoD, birthright, and approval requirements | Managed access policy | Sag | TBD | 2027-12-13 | 2027-12-24 | TO DO | Inputs: P5.11e/f birthright decisions; privileged treatment owned by P3 Standard (former P8.10 removed)
PAM - P8.11 | Review and apply approved managed-access requirements | SailPoint / Entra | Sag | TBD | 2027-12-27 | 2028-01-11 | TO DO
Review & approval by Security Governance
PAM - P8.12 | Prepare controlled review versions | Governance pack | Sag | TBD | 2028-02-01 | 2028-02-07 | TO DO
PAM - P8.13 | Distribute review pack and track comments | Governance pack | Sag | TBD | 2028-02-08 | 2028-02-15 | TO DO
PAM - P8.14 | Resolve business, technical, risk, and compliance comments | Governance pack | Sag | TBD | 2028-02-16 | 2028-02-25 | TO DO
PAM - P8.15 | Prepare final approval versions | Governance pack | Sag | TBD | 2028-02-28 | 2028-03-02 | TO DO
PAM - P8.16 | Obtain Security Governance approval | Security Governance | Sag | TBD | 2028-03-03 | 2028-03-09 | TO DO
Publish & communicate the policies
PAM - P8.17 | Publish approved documents in the controlled repository | Repository | Sag | TBD | 2028-03-13 | 2028-03-15 | TO DO
PAM - P8.18 | Prepare and deliver stakeholder communications | Comms | Sag | TBD | 2028-03-16 | 2028-03-23 | TO DO
PAM - P8.19 | Update supporting procedures and templates | Procedures | Sag | TBD | 2028-03-24 | 2028-03-31 | TO DO
PAM - P8.20 | Establish exception reporting | Governance | Sag | TBD | 2028-04-03 | 2028-04-07 | TO DO
PAM - P8.21 | Establish periodic review calendar | Governance | Sag | TBD | 2028-04-10 | 2028-04-12 | TO DO | Closes Roadmap Phase 3 / program
Legend:
Completed
In_Progress
In_Review
Blocked
Non-human account focus
Editable cells: Responsible User / Execution Owner (currently placeholders), Status, Roadblock/Dependencies. Dates for TO DO items are planned; update Start/End as work begins.